## Slide 1: CCC 145 – SANITARY DRAIN pipe STACK REPLACEMENT PLAN
www.kellerengineering.com
PRESENTED BY: CHRIS O’BRIEN, P.ENG. KELLER ENGINEERING OTTAWA / TORONTO
Calgary / Edmonton

## Slide 2: SANITARY RE-PIPING PROGRESS
YOUR CONDOMINIUM ENGINEERS
Sanitary piping replacement on P1 level has been completed
Proposed phasing schedule for sanitary stack piping replacement has been completed
Design and specifications for the sanitary stack piping replacement are underway and being finalized by year end
Ultrasonic thickness testing of domestic water riser piping has been completed and we are currently waiting for the results

## Slide 3: WHATS NEXT
YOUR CONDOMINIUM ENGINEERS
Project ready to tender in January 2024.
Construction could start as early as May 2024 (Dependent on Contractor availability)
Fixtures (Sinks, toilets, bathtubs, etc.) in the affected locations will not be useable for the duration of the stack replacement. Estimated 2 months per stack.
Phase 1 – no owner removals required. All wall openings will be performed from the corridors.
Recommend at least 1 month notice to owners of service shutdown, and a minimum 3 months notice when owner removals are required.

## Slide 4: ACCESS LOCATIONS
YOUR CONDOMINIUM ENGINEERS
Planning priority
  Minimize cost to the Corporation
  Minimize overall impact to occupants
Prioritize access from common corridors where possible to minimize construction cost and occupant impact
Where corridor access is not possible, access must be made available from within the suite served by the stack
In suite pipe access will require removal of fixtures and finishes by the owners
Wall openings for stack access will be made from the same side on each floor

## Slide 5: CONSTRUCTION REMOVALS PROCESS
YOUR CONDOMINIUM ENGINEERS
Prior to construction owners of affected suites will be notified with specific scheduling and any removals they are responsible for.
Removals (by owner)
  In suite removals to include toilets, sinks, bathtubs, tiles, and anything else on the effected wall or within the work area.
  Must be completed 2 weeks prior to start of construction. Suite inspections to verify removals are complete.
Removals (by Corporation)
  Drywall - type 2 asbestos abatement required
  Removal of old stacks and branch piping
  Chipping old mortar from around stacks and p-traps.

## Slide 6: CONSTRUCTION INSTALLATION PROCESS
YOUR CONDOMINIUM ENGINEERS
Installations (by Corporation)
  Stacks and branch piping
  Fire stopping material
  Drywall finished to a primed surface
Installations (by owner)
  Reinstate all fixtures and finishes in effected room.

## Slide 7: PHASING
YOUR CONDOMINIUM ENGINEERS
Prioritize early access from common corridors
  Maximizes notification to homeowners so they can coordinate contractors to have finishes removed
  First stacks serve to identify challenges and any site-specific conditions that may affect scheduling.
One stack per unit per phase
  Ensures adequate time for owners to re-instate washroom/kitchen fixtures before work begins on another stack affecting the suite

## Slide 8: PHASE 1 2024
YOUR CONDOMINIUM ENGINEERS
01 suites washroom 1
02 suites washroom 1
06 suites washroom 1
07 suites washroom 1
10 suites washroom 1
Laundry room floors 2-14

## Slide 9: PHASE 1 2024
YOUR CONDOMINIUM ENGINEERS
01, 02, 07, 10 suites washroom 1
  Corridor access.
06 suites washroom 1
  Corridor access floors 2-14, ground floor laundry ceiling and wall access.
Laundry room floors 2-14
  Laundry room access 2-14, ground floor corridor access.

## Slide 10: PHASE 2 2025
YOUR CONDOMINIUM ENGINEERS
01 suites washroom 2
02 suites washroom 2
06 suites kitchens
07 suites washroom 2
10 suites washroom 2
11 suites washroom 1

## Slide 11: PHASE 2 2025
YOUR CONDOMINIUM ENGINEERS
01, 02, 07, 10 suites washroom 2
  Corridor access.
06 suites kitchens
  Corridor access floors 2-14, ground floor storage room access.
11 suites washroom 1
  11 suites living room access.

## Slide 12: PHASE 3 2026
YOUR CONDOMINIUM ENGINEERS
03/04 suites washroom 2 floors 2-14
05 suites washroom 1
06 suites washroom 2
08 suites washroom 2
09 suites washroom 2
11 suites washroom 2 and kitchen

## Slide 13: PHASE 3 2026
YOUR CONDOMINIUM ENGINEERS
03/04 suites washroom 2 floors 2-14
  04 suite washroom 2 access from 2-14, ground floor closet access in 04 suite.
05 suites washroom 1
  05 suites washroom 1 access.
06 suites washroom 2
  06 suites washroom 2 access floors 2-14, ground floor storage room access.
08, 09 suites washroom 2
  08, 09 suites washroom 2 access.
11 suites washroom 2 and kitchen
  11 suite kitchen access.

## Slide 14: PHASE 4 2027
YOUR CONDOMINIUM ENGINEERS
01 Suites kitchens
02 Suites kitchens
03 suites washroom 1
04 suites washroom 1
05 Suites washroom 2
08 suites washroom 1
09 suites washroom 1

## Slide 15: PHASE 4 2027
YOUR CONDOMINIUM ENGINEERS
01 Suites kitchens
  01 suites den access.
02 Suites kitchens
  02 suites kitchen access
03, 04, 08, 09 suites washroom 1
  03, 04, 08, 09 suites washroom 1 access
05 Suites washroom 2
  05 suites washroom 2 access

## Slide 16: PHASE 5 2028
YOUR CONDOMINIUM ENGINEERS
03 Suites kitchens
04 Suites kitchens
05 Suites kitchens
07 Suites kitchens
08 Suites kitchens
09 Suites kitchens
10 Suites kitchens

## Slide 17: PHASE 5 2028
YOUR CONDOMINIUM ENGINEERS
03, 04, 05, 08, 09, 10 Suites kitchens
  03 , 04, 05, 08, 09, 10 suites kitchen access.
07 Suites kitchens
  07 suites kitchen access on all floors except 6, closet access on level 6.

## Slide 18: QUESTIONS?
YOUR CONDOMINIUM ENGINEERS
THANK YOU